## SoA
Schedule of Activity
Expected |  |  |  |  | Actual |  | Evaluation
Start | End | Description | Category | Parent deadline | Start_ | End_ | In duration | By end | Comment |  |  |  |  | Categories
2018-10-30 | 2018-10-31 | Write first draft of outline from brief and supervisor guidelines | Write-up | Preliminary Outline | 2018-10-30 | 2018-10-31 | YES | YES |  | YES | YES | 0 | 0 | Natural Language Processing
2018-10-31 | 2018-11-01 | Obtain feedback on outline from supervisor | Write-up | Preliminary Outline | 2018-10-31 | 2018-10-31 | YES | YES |  | YES | YES | 0 | 0 | User Interface and Visualisation
2018-10-31 | 2018-11-02 | Improve upon first draft using supervisor feedback | Write-up | Preliminary Outline | 2018-11-01 | 2018-11-02 | YES | YES |  | YES | YES | 0 | 0 | Law and context
2018-11-02 | 2018-11-02 | Submit preliminary outline to SAFE | Write-up | Preliminary Outline | 2018-11-02 | 2018-11-02 | YES | YES |  | YES | YES | 0 | 0 | Write-up
2018-11-05 | 2018-11-08 | Set up programming environment ready for data | Natural Lanuage Processing | Code | 2018-11-05 |  |  |  |  | YES | YES | 0 | 0
2018-11-08 | 2018-11-13 | Experiment with data and seed words to find other relevant words | Natural Lanuage Processing | Code | [5 empty] | YES | YES | 0 | 0
2018-11-05 | 2018-11-26 | Establish official requirements | Law and context | Preliminary Background Chapter | 2018-11-05 |  |  |  |  | YES | YES | 0 | 0
2018-11-05 | 2018-11-26 | Find out more about project context (what project will add to research and law in general) | Law and context | Preliminary Background Chapter | 2018-11-05 |  |  |  |  | YES | YES | 0 | 0
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Deadlines
Deadlines
Descirption | Self | Actual
Preliminary outline | 2018-11-02 | 2018-11-02
Preliminary background chapter | 2018-02-10 | 2018-02-11
Progress presentation | 2018-02-11 | 2018-02-11 | ?
Project fair poster | 2018-03-08 | 2018-03-08
Code | 2018-03-17 | 2018-05-15
Project thesis | 2018-05-12 | 2018-05-15

## Availability
My Availability
UniW | Week Start | Rating | Comment | Key | Meaning
6 | 2018-11-05 | 1 |  | 1 | 15+ hours spent on FYP
7 | 2018-11-12 | 1 |  | 2 | 10-14 hours spent on FYP
8 | 2018-11-19 | 2 |  | 3 | 5-9 hours spent on FYP
9 | 2018-11-26 | 3 | ML CW Friday
10 | 2018-11-03 | 3 | IPCV CW next Monday
11 | 2018-11-10 | 3 | HPC CW Friday
12 | 2018-11-17 | 1
C | 2018-12-24 | 2 | Family time and preparing for exams
C | 2018-12-31 | 2 | Family time and preparing for exams
C | 2018-01-07 | 3 | Preparing for exams (dependent on timetable)
JE | 2018-01-14 | 3 | Preparing for exams (dependent on timetable)
JE | 2018-01-21 | 2
13 | 2018-01-28 | 1
14 | 2018-02-04 | 1
15 | 2018-02-11 | 2
16 | 2018-02-18 | 2
17 | 2018-02-25 | 2
18 | 2018-03-04 | 2
19 | 2018-03-11 | 2
20 | 2018-03-18 | 2
21 | 2018-03-25 | 2
22 | 2018-04-01 | 2
EB | 2018-04-08 | 2
EB | 2018-04-15 | 2
EB | 2018-04-22 | 2
23 | 2018-04-29 | 2
24 | 2018-05-06 | 2